## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
1 | 1 | US01 | Set up the integrated Intelligent Bug Diagnosis Platform architecture and module structure | Must Have | Project setup | Snehali Dey | Completed
1 | 1 | US02 | Build React-based user interface and navigation for the integrated platform | Must Have | US01 | Pavithra N | Completed
1 | 1 | US03 | Preprocess raw bug reports and extract structured bug information for diagnosis | Must Have | US01 | Vaishali A | Completed
1 | 1 | US04 | Implement FastAPI backend services and API integration for bug analysis | Must Have | US01 | Chintakula Mahita Sri | Completed
2 | 2 | US05 | Implement Triage Agent to classify severity, priority and affected component | Must Have | US03, US04 | Tanvi Mitta | Completed
2 | 2 | US06 | Implement Log Analysis Agent to parse logs, exceptions and failure points | Must Have | US03, US04 | Venkata Vamsi | Completed
2 | 2 | US07 | Build historical bug Knowledge Vault for resolved cases and reusable knowledge | Must Have | US03 | Bobba Poorna Gopal | Completed
2 | 2 | US08 | Implement RAG retrieval over historical bug knowledge for contextual diagnosis | Must Have | US07 | Chembeti Eswar Rao | Completed
2 | 2 | US09 | Implement Root Cause Agent using parsed evidence and retrieved historical context | Must Have | US06, US08 | Sanjay N | Completed
3 | 3 | US10 | Implement Duplicate Detection Agent to identify semantically similar historical bugs | Must Have | US07, US08 | Kanishkhan J | Completed
3 | 3 | US11 | Implement Remediation Agent to recommend fix approaches from diagnosis and history | Must Have | US09, US10 | Vikaasni Selvakumar | Completed
3 | 3 | US12 | Develop dashboard and bug history views for diagnosis results and project visibility | Should Have | US02, US04 | Vansh Jain | Completed
3 | 3 | US13 | Develop Knowledge Vault interface for browsing historical bug cases and resolutions | Should Have | US07, US02 | Anirudh Sharma | Completed
4 | 4 | US14 | Integrate AI Copilot for natural-language interaction with diagnostic information | Should Have | US08, US11 | Yarakalapudi Vinay | Completed
4 | 4 | US15 | Integrate Cognitive Terminal for command-based interaction with diagnostic functions | Could Have | US04, US12 | Vishal Kumar | Completed
4 | 4 | US16 | Perform end-to-end integration testing, validation and issue fixing across modules | Must Have | US05-US15 | Macheneni Jahnavi | Completed
4 | 4 | US17 | Prepare final documentation, project guide, presentation and deployment-ready repository | Must Have | US16 | Boppana Srihitha | Completed

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
INTEGRATED PROJECT SPRINT BACKLOG
US01 | T01 | Set up the integrated Intelligent Bug Diagnosis Platform architecture and module structure | 2026-07-23 | 2026-07-28 | Snehali Dey | Architecture & setup | Completed | 8 | 6.9 | 5.7 | 4.6 | 3.4 | 2.3 | 1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US02 | T02 | Build React-based user interface and navigation for the integrated platform | 2026-07-24 | 2026-07-31 | Pavithra N | Frontend development | Completed | 8 | 6.9 | 5.7 | 4.6 | 3.4 | 2.3 | 1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US03 | T03 | Preprocess raw bug reports and extract structured bug information for diagnosis | 2026-07-29 | 2026-08-04 | Vaishali A | Bug preprocessing | Completed | 8 | 6.9 | 5.7 | 4.6 | 3.4 | 2.3 | 1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US04 | T04 | Implement FastAPI backend services and API integration for bug analysis | 2026-07-29 | 2026-08-05 | Chintakula Mahita Sri | Backend/API development | Completed | 8 | 6.9 | 5.7 | 4.6 | 3.4 | 2.3 | 1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US05 | T05 | Implement Triage Agent to classify severity, priority and affected component | 2026-08-05 | 2026-08-10 | Tanvi Mitta | Agent development | Completed | 8 | 6.9 | 5.7 | 4.6 | 3.4 | 2.3 | 1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US06 | T06 | Implement Log Analysis Agent to parse logs, exceptions and failure points | 2026-08-05 | 2026-08-11 | Venkata Vamsi | Log parsing | Completed | 8 | 6.9 | 5.7 | 4.6 | 3.4 | 2.3 | 1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US07 | T07 | Build historical bug Knowledge Vault for resolved cases and reusable knowledge | 2026-08-07 | 2026-08-13 | Bobba Poorna Gopal | Knowledge-base preparation | Completed | 8 | 6.9 | 5.7 | 4.6 | 3.4 | 2.3 | 1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US08 | T08 | Implement RAG retrieval over historical bug knowledge for contextual diagnosis | 2026-08-10 | 2026-08-17 | Chembeti Eswar Rao | RAG retrieval | Completed | 8 | 6.9 | 5.7 | 4.6 | 3.4 | 2.3 | 1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US09 | T09 | Implement Root Cause Agent using parsed evidence and retrieved historical context | 2026-08-12 | 2026-08-20 | Sanjay N | Root-cause analysis | Completed | 8 | 6.9 | 5.7 | 4.6 | 3.4 | 2.3 | 1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US10 | T10 | Implement Duplicate Detection Agent to identify semantically similar historical bugs | 2026-08-14 | 2026-08-21 | Kanishkhan J | Similarity matching | Completed | 8 | 6.9 | 5.7 | 4.6 | 3.4 | 2.3 | 1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US11 | T11 | Implement Remediation Agent to recommend fix approaches from diagnosis and history | 2026-08-18 | 2026-08-25 | Vikaasni Selvakumar | Fix recommendation | Completed | 8 | 6.9 | 5.7 | 4.6 | 3.4 | 2.3 | 1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US12 | T12 | Develop dashboard and bug history views for diagnosis results and project visibility | 2026-08-20 | 2026-08-28 | Vansh Jain | Dashboard integration | Completed | 8 | 6.9 | 5.7 | 4.6 | 3.4 | 2.3 | 1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US13 | T13 | Develop Knowledge Vault interface for browsing historical bug cases and resolutions | 2026-08-24 | 2026-09-01 | Anirudh Sharma | Knowledge interface | Completed | 8 | 6.9 | 5.7 | 4.6 | 3.4 | 2.3 | 1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US14 | T14 | Integrate AI Copilot for natural-language interaction with diagnostic information | 2026-08-28 | 2026-09-05 | Yarakalapudi Vinay | AI assistant integration | Completed | 8 | 6.9 | 5.7 | 4.6 | 3.4 | 2.3 | 1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US15 | T15 | Integrate Cognitive Terminal for command-based interaction with diagnostic functions | 2026-09-01 | 2026-09-08 | Vishal Kumar | Developer terminal integration | Completed | 8 | 6.9 | 5.7 | 4.6 | 3.4 | 2.3 | 1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US16 | T16 | Perform end-to-end integration testing, validation and issue fixing across modules | 2026-09-06 | 2026-09-12 | Macheneni Jahnavi | Testing & integration | Completed | 10 | 8.6 | 7.1 | 5.7 | 4.3 | 2.9 | 1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US17 | T17 | Prepare final documentation, project guide, presentation and deployment-ready repository | 2026-09-10 | 2026-09-16 | Boppana Srihitha | Documentation & presentation | Completed | 10 | 8.6 | 7.1 | 5.7 | 4.3 | 2.9 | 1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
1 | Day 1 | Initial integration dependencies and repository structure were not fully aligned. | Agreed common React + FastAPI structure and module ownership.
1 | Day 5 | Differences in individual module inputs and outputs caused integration issues. | Standardized API payloads and structured bug data format.
2 | Day 1 | Historical bug data needed consistent fields for retrieval. | Normalized Knowledge Vault records and required metadata.
2 | Day 5 | Agent outputs needed to pass context reliably to the next stage. | Defined common response schema for the multi-agent pipeline.
3 | Day 1 | Duplicate matching and root-cause results needed clearer evidence. | Improved retrieval context and displayed supporting historical cases.
3 | Day 5 | Frontend views required consistent backend error handling. | Added validation and clearer API response handling.
4 | Day 1 | New AI Copilot and Cognitive Terminal features required integration testing. | Connected features to available diagnostic data and tested workflows.
4 | Day 5 | Final end-to-end issues and documentation gaps remained. | Completed regression testing, fixes, documentation and presentation review.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | 1 | 2026-07-23 | 2026-08-04 | Snehali Dey, Pavithra N | Use a shared architecture and API contract from the beginning. | Working with isolated assumptions between modules. | Clear task ownership and frequent code sync. | Standardized project structure and integration interfaces.
2 | 1 | 2026-07-23 | 2026-08-04 | Vaishali A, Chintakula Mahita Sri | Validate structured bug input before agent processing. | Passing incomplete bug data between components. | Reusable preprocessing and backend validation. | Added structured preprocessing checks and API validation.
3 | 2 | 2026-08-05 | 2026-08-20 | Tanvi Mitta, Venkata Vamsi | Maintain consistent agent response formats. | Using inconsistent output keys across agents. | Modular agent-based diagnosis workflow. | Aligned agent outputs for pipeline integration.
4 | 2 | 2026-08-05 | 2026-08-20 | Bobba Poorna Gopal, Chembeti Eswar Rao | Improve historical bug metadata for better retrieval. | Keeping incomplete historical records. | Knowledge-driven diagnosis and reusable resolutions. | Cleaned and structured Knowledge Vault entries.
5 | 3 | 2026-08-21 | 2026-09-01 | Sanjay N, Kanishkhan J, Vikaasni Selvakumar | Test duplicate detection and remediation with varied bugs. | Relying on only a few sample cases. | RAG retrieval and evidence-based recommendations. | Expanded test scenarios and validated retrieved matches.
6 | 4 | 2026-09-02 | 2026-09-12 | Vansh Jain, Anirudh Sharma, Yarakalapudi Vinay | Test AI Copilot and Cognitive Terminal against integrated data. | Adding features without end-to-end validation. | Developer-friendly interaction and dashboard visibility. | Performed integration and regression testing.
7 | 4 | 2026-09-02 | 2026-09-16 | Vishal Kumar, Macheneni Jahnavi, Boppana Srihitha | Keep final documentation synchronized with implementation. | Last-minute documentation updates. | Team review, demos and presentation preparation. | Completed final documentation, repository and presentation review.