## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
D-01 | Snehali Dey | 2026-08-10 | A Developer role user is able to open the Admin / Control Center route directly by entering the URL, and the workspace user list is rendered before the role check completes. | Sprint 1 | Snehali Dey | Logical | Role check moved to the backend endpoint and a protected route guard added on the frontend so the component does not mount for non-admin roles. | 2026-08-13 | Closed | Raised from UT-34. Retested with Developer, QA Engineer and Team Lead roles.
D-02 | Pavithra N | 2026-08-11 | Theme toggle does not persist. After a browser refresh the application reverts to the light theme even though dark was selected, and chart labels remain unreadable on the dark background. | Sprint 1 | Pavithra N | User Interface | Theme preference persisted in local storage and applied on app load; Chart.js label and grid colours bound to the active theme. | 2026-08-14 | Closed | Raised from UT-35.
D-03 | Chintakula Mahita Sri | 2026-08-18 | Insights page 30-day trend chart counts cases by creation date only, so cases resolved within the window are missing from the resolved series and the health score is overstated. | Sprint 2 | Chintakula Mahita Sri | Logical | Analytics query corrected to aggregate on both created and resolved timestamps; health score recomputed from the corrected series. | 2026-08-21 | Closed | Raised from UT-29. Verified against a seeded 30-day data set.
D-04 | Vaishali A | 2026-08-19 | Root Cause Agent returns a high confidence value even when no similar resolved case with resolution notes exists, which makes an unsupported root cause look historically grounded. | Sprint 2 | Vaishali A | Logical | Confidence calculation reweighted so historical grounding contributes only when a matching resolved case is found; UI now states when no historical evidence was available. | 2026-08-24 | Closed | Raised from UT-17.
D-05 | Tanvi Mitta | 2026-08-20 | Frontend cannot reach the backend when the API base URL is not configured. The app fails silently on the Overview page with an empty dashboard instead of reporting a connection error. | Sprint 2 | Tanvi Mitta | Others | API base URL read from the frontend environment configuration with a documented default of http://127.0.0.1:8000, and a connection-error banner added. | 2026-08-25 | Closed | Raised from UT-37. .env.example updated with the required variable.
D-06 | Venkata Vamsi | 2026-08-26 | Unsupported file types are accepted by the diagnosis upload control. A binary file is stored in the uploads folder and is then passed to the log parser, which produces meaningless evidence. | Sprint 3 | Venkata Vamsi | Standards | Server-side extension and MIME whitelist added for text, log and code files; rejected uploads return a clear validation message and are not written to disk. | 2026-08-29 | Closed | Raised from UT-10.
D-07 | Bobba Poorna Gopal | 2026-08-27 | When the AI provider key is missing or invalid, the analysis request fails with an unhandled exception and the case is left showing a permanent 'Analyzing' state with no error message. | Sprint 3 | Bobba Poorna Gopal | Logical | Exception handling added around the agent pipeline; the case reverts to its previous state and the UI shows the configuration error returned by the API. | 2026-09-01 | Closed | Raised from UT-38. Matches the troubleshooting entry for AI analysis failure.
D-08 | Chembeti Eswar Rao | 2026-09-02 | OCR text extraction from attached screenshots is not appended to the runtime evidence, so an error visible in the image is ignored by Log Intelligence and the Root Cause Agent. | Sprint 3 | Chembeti Eswar Rao | Logical | OCR output appended to the evidence payload before the pipeline runs, with a graceful skip and log entry when the OCR dependency is unavailable. | 2026-09-07 | Open | Raised from UT-25. Fix implemented; pending retest on a machine without the OCR dependency installed.
D-09 | Sanjay N | 2026-09-03 | Similarity results list the same historical bug more than once when a case has been analysed multiple times, because each analysis run is indexed separately. | Sprint 3 | Sanjay N | Logical | Similarity results de-duplicated by bug id, retaining the highest similarity percentage per case. | 2026-09-08 | Closed | Found during regression of UT-15.
D-10 | Kanishkhan J | 2026-09-04 | The sign-out menu in the top bar is overlapped by the page content on smaller screens, so the option cannot be clicked at widths below roughly 1280 px. | Sprint 4 | Kanishkhan J | User Interface | Top bar redesigned with a corrected stacking context and z-index; verified on 1024, 1280 and 1440 px widths. | 2026-09-09 | Closed | Listed in the troubleshooting section of the handover document.
D-11 | Vikaasni Selvakumar | 2026-09-07 | The PDF diagnostic report truncates long descriptions and remediation text to a single page instead of flowing onto the next page. | Sprint 4 | Vikaasni Selvakumar | User Interface | Report generation switched to a flowing layout with automatic page breaks and repeated section headers. | 2026-09-10 | Closed | Raised during UT-30 regression.
D-12 | Vansh Jain | 2026-09-08 | Agent modules repeat the same log-parsing and evidence-building code, which makes adding a new language pattern require edits in more than one place. | Sprint 4 | Vansh Jain | Maintainability | Shared parsing and evidence helpers extracted into a single utility module consumed by all five agents. | 2026-09-11 | Closed | Refactor only. No functional change; full UT pack re-executed.
D-13 | Anirudh Sharma | 2026-09-09 | Backend endpoints and SQLAlchemy models use inconsistent naming for the same field (bug_id and case_id), which is carried through into the API responses. | Sprint 4 | Anirudh Sharma | Standards | Naming standardised to case_id across models, schemas and endpoints; frontend service layer updated accordingly. | 2026-09-12 | Closed | Agreed naming convention documented in the backend README.
D-14 | Yarakalapudi Vinay | 2026-09-10 | Knowledge Vault shows resolved cases that have empty resolution notes, so entries appear in the vault without contributing any reusable knowledge. | Sprint 4 | Yarakalapudi Vinay | Logical | Vault query filtered to resolved cases with non-empty resolution knowledge; the resolve dialog now requires resolution notes before saving. | 2026-09-14 | Open | Fix in review. Retest scheduled with the Sprint 4 regression pass.
D-15 | Vishal Kumar | 2026-09-11 | Backend code changes are not reflected without a manual restart because uvicorn is started without the reload flag in the documented run command. | Sprint 4 | Vishal Kumar | Others | Handover documentation updated to note python -m uvicorn app.main:app --reload for development use, keeping the plain command for demo runs. | 2026-09-15 | Closed | Documentation change only.
D-16 | Macheneni Jahnavi | 2026-09-12 | Dashboard insight values needed period switching. | Sprint 4 | Macheneni Jahnavi | User Interface | Added Week/Month selection for dashboard metrics. | 2026-09-16 | Closed | The selected period controls displayed analysis data.
D-17 | Boppana Srihitha | 2026-09-13 | Light-theme text and cards had insufficient contrast. | Sprint 4 | Boppana Srihitha | User Interface | Increased text contrast and strengthened card outlines and hover states. | 2026-09-17 | Closed | Content remains readable in both themes.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others