## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
1 | 1 | US01 | As a developer, I want raw bug reports to be preprocessed so that important diagnostic information is extracted in a structured form. | Must Have | None | S VIKAASNI | Completed
1 | 1 | US02 | As a developer, I want exception type, priority, affected file, line number, keywords, and stack trace to be extracted from a bug report. | Must Have | US01 | S VIKAASNI | Completed
1 | 1 | US03 | As a developer, I want processed bug information to be saved as structured JSON for downstream analysis. | Must Have | US01, US02 | S VIKAASNI | Completed
2 | 2 | US04 | As a user, I want to upload PDF/TXT documents and extract their text for preprocessing and analysis. | Should Have | None | S VIKAASNI | Completed
2 | 2 | US05 | As a developer, I want basic NLP preprocessing such as tokenization, stop-word handling, stemming, lemmatization, and keyword extraction. | Should Have | US04 | S VIKAASNI | Completed
3 | 3 | US06 | As a user, I want a FastAPI backend endpoint to accept bug files/text and return analysis-ready structured data. | Must Have | US01-US05 | S VIKAASNI | Completed
3 | 3 | US07 | As a developer, I want API documentation through Swagger so that endpoints can be tested easily. | Should Have | US | S VIKAASNI | 3- Completed

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 49 | 17 | 17 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
NOTES: | Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
US01 | T01 | Preprocess raw bug reports and extract important diagnostic information | 17-09-2026 | 17-09-2026 | S VIKAASNI | Development | Completed | 4 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US02 | T02 | Extract exception type, priority, affected file, line number, keywords and stack trace | 17-09-2026 | 18-09-2026 | S VIKAASNI | Development | Completed | 6 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US03 | T03 | Store processed bug information as structured JSON | 18-09-2026 | 18-09-2026 | S VIKAASNI | Development | Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US04 | T04 | Implement PDF/TXT document upload and text extraction | 19-09-2026 | 19-09-2026 | S VIKAASNI | Development | Completed | 5 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US05 | T05 | Implement NLP preprocessing including tokenization, stop-word handling, stemming, lemmatization and keyword extraction | 20-09-2026 | 21-09-2026 | S VIKAASNI | Development | Completed | 8 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US06 | T06 | Develop FastAPI endpoint for bug file and text analysis | 22-09-2026 | 23-09-2026 | S VIKAASNI | Development | Completed | 8 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US07 | T07 | Configure Swagger API documentation and endpoint testing | 24-09-2026 | 24-09-2026 | S VIKAASNI | Development | Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US08 | T08 | Test preprocessing module using sample bug reports and error cases | 25-09-2026 | 26-09-2026 | S VIKAASNI | Testing | Completed | 6 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US09 | T09 | Document preprocessing module and prepare it for platform integration | 27-09-2026 | 27-09-2026 | S VIKAASNI | Documentation | Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | No major impediments | Completed initial bug report preprocessing tasks
Sprint 1 | Day 2 | Minor data formatting issues | Standardized input format and validated extracted fields
Sprint 1 | Day 3 | JSON structure validation issue | Updated JSON schema and tested structured output
Sprint 1 | Day 4 | PDF/TXT text extraction inconsistencies | Handled different document formats and improved text extraction
Sprint 1 | Day 5 | NLP preprocessing errors | Refined tokenization, stop-word removal, stemming and lemmatization
Sprint 1 | Day 6 | API input validation issue | Added input validation and tested FastAPI endpoint
Sprint 1 | Day 7 | Swagger endpoint configuration issue | Updated API documentation and verified endpoints
Sprint 1 | Day 8 | Test data and edge-case handling | Added sample bug reports and performed error-handling tests
Sprint 1 | Day 9 | Minor documentation gaps | Updated module documentation and integration details
Sprint 1 | Day 10 | No major impediments | Performed final testing and verified sprint deliverables

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
2 | 1 | 1 | 17-09-2026 | 27-09-2026 | S VIKAASNI | Plan tasks before development | Avoid delaying testing | Regular testing and documentation | Followed sprint plan and completed assigned tasks
3
4
5
6
7