## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | S VIKAASNI | 17-09-2026 | Summarized diagnostic information is not extracted correctly from some raw bug reports. | Sprint 1 | S VIKAASNI | Functional | Updated preprocessing logic and tested with multiple sample bug reports. | 18-09-2026 | Closed | Extraction verified after correction.
2 | S VIKAASNI | 17-09-2026 | Unsupported file types are not consistently rejected during upload. | Sprint 1 | S VIKAASNI | Validation | Added file-type validation and tested unsupported file formats. | 18-09-2026 | Closed | Invalid files are now rejected.
3 | S VIKAASNI | 17-09-2026 | Root cause output is limited when no historical bug data is available. | Sprint 1 | S VIKAASNI | AI/Functional | Improved fallback root-cause handling for cases without historical matches. | 19-09-2026 | Closed | Generic root cause is displayed with appropriate confidence.
4 | S VIKAASNI | 17-09-2026 | Insights dashboard charts may not display correct values for some case combinations. | Sprint 1 | S VIKAASNI | UI/Functional | Corrected analytics calculation and chart rendering logic. | 20-09-2026 | Closed | Analytics values verified with sample data.
5 | S VIKAASNI | 17-09-2026 | Non-admin users can access the Control Center route in some cases. | Sprint 1 | S VIKAASNI | Security | Added role-based route protection and verified unauthorized access handling. | 21-09-2026 | Closed | Non-admin access is now restricted.
6 | S VIKAASNI | 17-09-2026 | Dark and light theme selection is not consistently maintained across screens. | Sprint 1 | S VIKAASNI | UI | Updated theme state handling and persistence across application pages. | 22-09-2026 | Closed | Theme remains consistent after navigation and refresh.
7 | S VIKAASNI | 17-09-2026 | Frontend occasionally fails to communicate with the FastAPI backend. | Sprint 1 | S VIKAASNI | Integration | Checked API configuration, CORS settings and frontend backend connection. | 23-09-2026 | Closed | Frontend and backend communication verified.
8 | S VIKAASNI | 17-09-2026 | AI diagnosis does not provide a clear response when the AI provider API key is unavailable. | Sprint 1 | S VIKAASNI | Error Handling | Added AI configuration error handling and user-friendly error messages. | 24-09-2026 | Closed | Failure is handled without corrupting case data.
9 | S VIKAASNI | 17-09-2026 | OCR text extraction from uploaded screenshots is not working correctly. | Sprint 1 | S VIKAASNI | OCR/Functional | Updated OCR processing and tested image-based error messages. | 25-09-2026 | Closed | OCR extraction verified with sample screenshots.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others